## Goals
SPRINT | GOALS
1 | Design a wireframe
Design a Logo
Database setup
Create group on microsoft teams
Work on trello boards
| ` | 1 | 1
2 | Finish Basic structure of wireframe
Finish Landing page, contact, other breadcrumbs
Start applying Javascript for validation on user inputs
Link the database with the website inputs
membership form
Adding data to trainers table
3 | Lorem Ipsum | April 2th
Lorem Ipsum
| Lorem Ipsum | April 3rd
Lorem Ipsum
| Lorem Ipsum | April 9th
Lorem Ipsum
4 | Lorem Ipsum
Lorem Ipsum
Lorem Ipsum
Lorem Ipsum
Lorem Ipsum
Lorem Ipsum
Lorem Ipsum
Please check the next sheet for Sprint BurnDown

## Sprint BurnDown
Sprint 1 (Time In Hours)
Tasks | Assigned to | Time | Status
GOAL
Design a wireframe | Shiwani | 4 | Completed
Design a logo | Daljeet, Shiwani, Ramandeep |  | Completed
Database set up | Ramandeep Kaur | 5 | Completed
Look for other requirement | Daljeet, Shiwani, Ramandeep | 4 | Completed
Sprint 2 (Time In Hours)
Tasks | Assigned to | Time | Status
GOAL - Lorem Ipsum
Finish Basic structure of wireframe | Ramandeep Kaur, Shiwani | 1 | Completed
Finish Landing page, contact, other breadcrumbs | Ramandeep, Shiwani, Daljeet | 1 | Completed
Start applying Javascript for validation on user inputs | Daljeet | 3 | Completed
Adding trainer list | shiwani | 1 | In Progress
membership from | Ramandeep Kaur | 2 | Completed
Sprint 3 (Time In Hours)
Tasks | Assigned to | Time | Status
GOAL - Lorem Ipsum
Lorem Ipsum | abc, pqr, xyz | 1 | In Progress
Lorem Ipsum | xyz | 1 | Completed
Lorem Ipsum | pqr | 0.5 | Due
Lorem Ipsum | abc, pqr, xyz | 0.5 | Completed
Lorem Ipsum | pqr, xyz | 1 | Completed
Lorem Ipsum | abc, pqr, xyz | 1 | Completed
Lorem Ipsum | pqr, xyz | 2 | In Progress
Lorem Ipsum | abc, pqr, xyz | 1 | In Progress
GOAL - Lorem Ipsum
Lorem Ipsum | xyz | 0.5 | In Progress
Lorem Ipsum | pqr | 1 | In Progress
Lorem Ipsum | abc, pqr, xyz | 2 | In Progress
Lorem Ipsum | pqr, xyz | 0.5 | In Progress
Sprint 4 (Time In Hours)
Tasks | Assigned to | Time | Status
GOAL - Lorem Ipsum
Lorem Ipsum | abc, pqr, xyz | 1 | In Progress
Lorem Ipsum | xyz | 1 | Completed
Lorem Ipsum | pqr | 0.5 | Due
Lorem Ipsum | abc, pqr, xyz | 0.5 | Completed
Lorem Ipsum | pqr, xyz | 1 | Completed
Lorem Ipsum | abc, pqr, xyz | 1 | Completed
Lorem Ipsum | pqr, xyz | 2 | In Progress
Lorem Ipsum | abc, pqr, xyz | 1 | In Progress
GOAL - Lorem Ipsum
Lorem Ipsum | xyz | 0.5 | In Progress
Lorem Ipsum | pqr | 1 | In Progress
Lorem Ipsum | abc, pqr, xyz | 2 | In Progress
Lorem Ipsum | pqr, xyz | 0.5 | In Progress
Please check the next sheet for Product Backlog

## Product Backlog
ID | Description | Sprint
23 | Adding trainer list | 2
Please check the next sheet for Challenges

## Challenges
Challenges Faced | Time Invested | Status | Solution
Challenge faced during using photoshop | Half an hour | Solved | Used Remote login of conestoga college through VPN
Lorem Ipsum | 4 days | Solved | Lorem Ipsum
Lorem Ipsum | 30 minutes | Solved | Lorem Ipsum
Lorem Ipsum | 45 minutes | Solved | Lorem Ipsum
Lorem Ipsum | 10 days and still on | In Progress